## excel (10)
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Project Settings
Project Owner | Edgar Alexander Aguilar BolaÃ±os
Start Date | mar 20, 2017 05:07:21 PM
Completion Date | mar 21, 2017 11:51:54 AM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | To Date
Size/Hour | 39.1 | 22.4 | 33.8
Planned Time | 0.20417 |  | 0.99583
Actual Time |  | 0.25625 | 1899-12-31 03:19
CPI (Cost-Performance Index) |  |  | 0.87
% Reuse | 13.5% | 15.3% | 8.2%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 16.6 | 7.25 | 15.2
Total Defects/KLOC or equivalent | 34.4 | 29 | 33.6
Yield % | 51.9% | 75% | 54.8%
Code Review Rate | 1908 | 414 | 1203
Program Size
| Plan | Actual | To Date
Base (B) | 172 | 172 | 342
Deleted (D) | 0 | 0 | 2
Modified (M) | 3 | 1 | 6
Added (A) | 188 | 137 | 916
Reused (R) | 56 | 56 | 97
Added and Modified (A+M) | 191 | 138 | 922
Total Size (T) | 416 | 365 | 1183
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 172 | 386 | 906
Time In Phase
| Plan | Actual | To Date | To Date %
Planning | 0.05 | 0.072917 | 0.28889 | 25.4%
Design | 0.027778 | 0.045139 | 0.16458 | 14.5%
Design Review | 0.00069444 | 0.0055556 | 0.0090278 | 0.79%
Code | 0.0625 | 0.075694 | 0.34514 | 30.3%
Code Review | 0.0041667 | 0.013889 | 0.031944 | 2.81%
Compile | 0 | 0.00069444 | 0.0013889 | 0.12%
Test | 0.034028 | 0.021528 | 0.16736 | 14.7%
Postmortem | 0.025 | 0.020833 | 0.12986 | 11.4%
Total | 0.20417 | 0.25625 | 1899-12-31 03:19
Defects Injected
| Plan | Actual | To Date | To Date %
Before Development | 0 | 0 | 0 | 0%
Planning | 0.49 | 0 | 2 | 6.45%
Design | 2.2 | 1 | 10 | 32.3%
Design Review | 0 | 0 | 0 | 0%
Code | 3.9 | 3 | 19 | 61.3%
Code Review | 0 | 0 | 0 | 0%
Compile | 0 | 0 | 0 | 0%
Test | 0 | 0 | 0 | 0%
Total | 6.59 | 4 | 31
Defects Removed
| Plan | Actual | To Date | To Date %
Planning | 0 | 0 | 0 | 0%
Design | 0.24 | 0 | 1 | 3.23%
Design Review | 0 | 0 | 0 | 0%
Code | 2.2 | 1 | 10 | 32.3%
Code Review | 0.98 | 2 | 6 | 19.4%
Compile | 0 | 0 | 0 | 0%
Test | 3.17 | 1 | 14 | 45.2%
Total | 6.59 | 4 | 31
After Development | 0 | 0 | 0
Defect Removal Efficiency
| Plan | Actual | To Date
Defects/Hour - Design Review | 0 | 0 | 0
Defects/Hour - Code Review | 9.73 | 6 | 7.83
Defects/Hour - Compile | 0 | 0 | 0
Defects/Hour - Test | 3.92 | 1.94 | 3.49
DRL (DLDR/UT) | 0 | 0 | 0
DRL (Code Review/UT) | 2.49 | 3.1 | 2.25
DRL (Compile/UT) | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Report generated at 08:30 AM on 22/03/2017