## excel (12)
Project/Task | Phase | Start Time | Delta | Interrupt | Comment
/Non Project/PSP Fundamentals & Advanced/Program 4 | Planning | mar 20, 2017 05:07:21 PM | 45 | 3
/Non Project/PSP Fundamentals & Advanced/Program 4 | Planning | mar 20, 2017 06:27:49 PM | 22 | 39
/Non Project/PSP Fundamentals & Advanced/Program 4 | Planning | mar 20, 2017 07:36:31 PM | 38 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Design | mar 20, 2017 08:14:02 PM | 35 | 51
/Non Project/PSP Fundamentals & Advanced/Program 4 | Design | mar 20, 2017 10:18:18 PM | 30 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Design Review | mar 20, 2017 10:47:59 PM | 8 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Code | mar 20, 2017 10:56:18 PM | 1 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Code | mar 21, 2017 07:03:42 AM | 42 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Code | mar 21, 2017 07:56:50 AM | 66 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Code Review | mar 21, 2017 09:02:51 AM | 19 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Code Review | mar 21, 2017 09:37:06 AM | 1 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Compile | mar 21, 2017 09:37:24 AM | 1 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Test | mar 21, 2017 09:38:53 AM | 6 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Test | mar 21, 2017 10:02:56 AM | 3 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Test | mar 21, 2017 10:59:28 AM | 22 | 0
/Non Project/PSP Fundamentals & Advanced/Program 4 | Postmortem | mar 21, 2017 11:21:32 AM | 30 | 0